## Slide 1
FM3/FM4 Status GLM Science Team Meeting
Marc Rafal
GLM Instrument Manager
21 September 2021
Drawing Not To Scale
Never thought it would last this long

## Slide 2: GOES-T/U Update
GOES-T
  All environmental tests completed
  Storage in Waterton until shipment
  Ship to Cape November 2021
  Launch now February 16, 2022
    Delayed due to Starliner launch delay
GOES-U
  GLM FM4 in storage at Waterton
  Environmental testing Starts early 2023
  Ship to Cape December 2023
  Launch April 2024 (tentative)
  SpaceX Falcon Heavy selected for GOES-U launch vehicle
GOES-T Configured for Storage

## Slide 3: FM3
Performance improvements compared to FM1/2
  Design changes to mitigate
    Stray light from solar intrusion
    Overshoot/undershoot at high contrast boundaries
  Improved camera timing settings
    Longer “Triple Wide DC Restore” pulse results in lower noise
    Allows lower RTEP Thresholds yielding higher DE
    Evaluating use on FM1 and FM2 on-orbit
  Tewa Kaplun will cover predicted performance

## Slide 4: FM4
FM4 completed all instrument level environmental tests
Delivered to Waterton
  Bench acceptance test completed
  In storage in High Bay until installation on GOES-U
EU Installation scheduled October 2021
SU Installation scheduled early 2022
Tewa Kaplun will cover predicted performance

## Slide 5: On-Orbit Status
FM1 (GOES-E) and FM2 (GOES-W) continue to operate nominally
GOES-W entered safe hold July 22, 2021 and returned to operation July 23
  Double bit memory error in spacecraft computer
  GLM returned to Normal Mode after spacecraft restart
    Tested new Loop Heat Pipe Startup Macro
Collected on-orbit data on FM2 (GOES-W) with Triple Wide DC Restore
  Confirmed lower noise
  Executed first iteration on RTEP threshold setting
  Once iterations complete will evaluate DE improvement and make a recommendation on operational change for FM1 and FM2